CCE minutes

March  2026

Accounts

Current Balance -Bank Account £6986.02, Cash £120  since paid £1000 to lt audio

Restricted funds   Shed funding £1614.2

Mama Mia  £1500

Kpop	£630 ( balance)

Marquee (Helen Main) £1319.54

Bank Account Verification 2023-2024 and 2024-2025 ready to be verified

Crail Fest Planning

- Licenses

All applied for , Natasha doing market license . Alcohol granted . Public entertainment applied for but won’t be granted until nearer the time

- Tickets

Sold 148 online and a note of other 16 , free tickets or food vouchers for houses that back onto park  and  free tickets for penams , limit 500 but Fiona to check with Fife Council in case extra security needed

- Timings

Friday entry 4.30, 1st band 5pm. Volunteers needed to check tickets and issue wristbands, security and bar to look out for anyone without a band .  last orders 9.30 Friday. Saturday 11 am last orders 7.30pm.

Food vans out with ticket area to allow anyone to get food

- Funding

confirmed £500 kingdom housing, crowdfunder fife council £2000, Penmans and other sponsors. Windfarm applied but not sure if they still do the funding as there is another community fund that the partnership got , settlement trust to be applied for in new financial year to cover half price wrist bands for local kids . Fiona to pay sponsorship money into the crowdfunder and £100 from budd bites.

- Costs

Pay in advance as must as possible, Fiona donating balloons and decorations to help costs

- Market

30 booked hoping for 50, a good mix ( asking for list to see if we can help increase)

Email all previous stall holders that haven’t applied

- Kids activities

Depending on funding look at getting 2 children’s rides with cost covered by ourselves but included in wrist bands, fiona to investigate cost of fun performers and other children’s stalls. Jamie jester to get a gazebo plus roam about.

Cee cee entertainments putting up some inflatables on Friday and Tony Bell bringing toy stall Saturday

- Volunteers

Social media push to try get some extra help especially with set up and clear down. Kelvin to sort bar staff

- Extras

Hoodies, t shirts Orange t shirts and navy hoodies

- Leaflets, advertising

cheap leaflet like last year plus a proper brochure with sponsors and adverts depending on costs . More printed posters and big signs and banners. Fiona meeting with welcome to Fife

- Dog Show

need judges plus someone to man on day , host in other marquee. Megan to ask Fido to take registration details and dawns kennels for judging. Make it more a dog show

- Charity stalls

beat goalie by Crail United and springer rescue confirmed put out on socials to see if other local groups would like a charity space

- Site map

Burger van to move nearer beer tent, try enclose off as much space as possible for Friday night

- Car parking Roger to speak to Killfedder

- Tickets on day price £20

- Penmans  Friday night food, history storyboard, voucher hunt,

- Raffle drawn automatic at 5pm and prizes there for collection . separate cash raffle on day with 3 prizes

Other stuff

Ask Penmans to judge fancy dress before 1st band

Crowning at Shoregate with old time sailors ( TBC )

Speak to airfield about car for king and queen transport and parade

Abba

- Volunteers 4 in kitchen could do with another 3 waitresses

- Menu and ordering. Tracey, Diane and kelvin doing cakes. Sausage rolls butchers, bread Morrisons and fillings Budds bites. Roger to sort out orders and amounts

- Timings and plan start at 2 in hall from 10am, Fiona sorting decorations and fizz

- Set up and clear down times. Extend times with hall so not rushed to clear up

Kpop

- Set up and supervising names to Fiona

- Tuck shop ideas juice, popcorn, pick a mix

Clubland

Low ticket sales cancel and move to September

Christmas

- Band needed wait till after Crail fest and check availability with number 1 sun and danger zone

- Pre-registration

Dates 28th November party , Santa 5th December 6 tables pre-registered

Aob

Trademark currently no update the tm8 is in and no contact from Crail Festival

Beach Library needs re stocked , fiona has a small amount but more needed

Christmas lights and lamp posts. Fife council asked for a full report by 4th April with all lamp numbers, signage attached , hanging basket plus details of all motifs we have

Shed update, waiting on Doug to put in planning still , installation end of June

Things needing done

Raffle put online Fiona to do

Insurance updated and checked. Have separate event insurance for Crail Fest in case of bad weather ,

Need to book pizza van and ice cream van

Kelvin to book generator and black box

Glitter/face painter Friday Night

Order headsets for walkie talkies and litter pickers

3 x gazebos for food van cover/ stage

A few more committee members needed, social media post to go out

Photographer/ videographer needed for both days ( help with 2027 advertising )

Bar stock on sale or return via Allsons, kelvin to do orders

Roger speaking to Barnetts about more pumps for bar

Seats from town hall to go to shed once new one is installed ( need bodies to move )